## Jorge Crew
Project: | INSTALL STR-1/18" SD AND STR-2
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Gray Bricks |  | 1 Pallet | Y | Lay Area 1 | 2026-06-17 | 2026-06-19
| Filter Fabric | 1 Roll | 1 Roll | Y
| Black Paint | 5 Gallons |  | Y | Conex 4
| Portland Cement | 5 Bags | 5 Bags | Y | Storage Area 2 | 2026-06-17 | 2026-06-19
| Sand | 10 Bags | 10 Bags | Y | Storage Area 2 | 2026-06-17 | 2026-06-19
Project: | 12" UW South of New Chem Trench
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| 6" Megalugs |  |  | Y | Lay Area 2
| 6" Bolt Kits |  |  | Y | Lay Area 2
| 12" Megalugs | 2 | 12 | Y | John | 2026-06-23
| 12" Bolt Kits | 12 | 12 | Y | Lay Area 2
| 6" x 2" MJ NPT Plug | 1 | 1 | Y |  | 2026-07-01
Project: | 4" UW Line
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Blue Bolt Kits |  |  | N | John | 2026-07-20
Project:
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date

## Erid's Crew
Project: | D-Curb and Gutter
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| 2x8 | 10 |  | Y | Near Work Site
| Rebar | ~ |  | Y | Near Work Site
| Bricks | ~ |  | Y | Near Work Site
| Sikaflex 1A | ~ |  | Y | Conex 1
| Curing Compound | 5 Gallon Bucket | 5 Gallon Bucket | Y | Conex 1 | 2026-06-18 | 2026-06-19
| Snap Cap | 200 Feet | 200 Feet | Y | Conex 1 | 2026-06-16 | 2026-06-17
| 6" Concrete Edger | 1 | 1 | Y | Erid's Crew | 2026-06-17 | 2026-06-18
| 2" Concrete Nails |  | 1 Box | Y | Conex 1 | 2026-06-15 | 2026-06-23
| 2' Metal Pins w/holes for Nails | 60 | 60 |  | Erid's Crew | 2026-06-17 | 2026-06-18
Project:
Slide gate
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Plywood |  |  | Y | Offsite Storage location
| 2x4x16 |  |  | Y | Near Conex 2
| No Shrink grout | 32 | 32 | Y | Storage Area 2 + on site | 2026-06-12 | 2026-06-14
| All threaded Stud 1/2" NC x 17" LG | 6 |  | Y | WS Field Office
| All threaded Stud 1/2" NC x 12 1/2" LG | 34 |  | Y | WS Field Office
| Hilti Epoxy |  |  | Y | Garney Field Office
| Drill Bits 9/16" |  |  | Y | WS Field Office
| 1/2" x 1 1/4" Washer |  |  | Y | WS Field Office
| 1/2" - 13 NC Nut |  |  | Y | WS Field Office
Project:
Transformer Pad
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Rebar Bender #5 Bar |  | 1 | Y | Conex 1 | 2026-06-18 | 2026-06-19
| #5 Rebar | 1500 Feet | 1500 Feet | Y | Erid's Crew | 2026-06-24 | 2026-06-25
| 6" x 5'Upper Continuous Slab Bolster | 10 | 10 | Y | Erid's Crew | 2026-06-24 | 2026-06-25
Project: | Gravity Wall
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Rebar | ? | ?
| Plywood | ? | ?
| 1/4" x 3-1/4" Tap Screws | 1 | 1 | Y |  | 2026-07-13 | 2026-07-16
Project: | D-Curb
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
Project:
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date

## Smoot's Crew
Project: | Roof Drains
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| 5/8" Concrete Drill Bit | 3 | 3 | Y |  | 2026-06-16 | 2026-06-18
| 6" Bolt Kits | 100 | 64 | Y | Conex 3
| 4" Bolt Kits | 47 | 40 | Y | Conex 3
| 6"X3" Filler Flange | 4 | 2 | Y | Storage Yard
| 4" Mega Flange | 8 | 8 | Y
| 6" Mega Flange | 6 | 11 | Y | Storage Yard 2
| Bucket Harness | 2 | 2 | Y | Conex 1 | 2026-06-18 | 2026-06-23
| 5 Gallon Bucket | 6 | 6 | Y | Conex 2 | 2026-06-17 | 2026-06-18
| Yellow Sponges | 5 | 5 | Y | Conex 1 | 2026-06-17 | 2026-06-23
| Flange by Plane End Piece |  | 1 | N | John | 2026-07-22
| Pipe (90) |  | 1 | N | John | 2026-07-22
Project:
Steel Plate for FI Test
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Rebar Eater 7/8" | 6 | 6 | Y | Conex 1 | 2026-06-16 | 2026-06-17
| Rebar Eater 3/4" | 10 | 6 | Y |  | 2026-06-16 | 2026-06-29
| Rebar Eater 1" | 3 | 3 | Y | Conex 1 | 2026-06-16 | 2026-06-18
| 3/4"x 8.5" Wedge Anchors | 30 | 23 | Y | Smoot's Gangbox | 2026-06-15 | 2026-06-18
| 3/4"x 8.5" Wedge Anchors | 30 | 30 | Y |  | 2026-06-24 | 2026-07-01
| 20 oz Sikaflex Sealant | 6 | 6 | Y |  | 2026-07-09 | 2026-07-09
| Concrete Rust Remover |  |  | N
| Hydraulic Cement Buckets |  | 2 | N
Project:
Troughs
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Fiberglass Troughs |  |  | Y
Project:
Junction Box 2
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| 30" Bolts + Nuts -> 1.25" x 6.5" |  | 14 | Y |  | 2026-06-25 | 2026-07-14
| 5 Gallon Buckets |  | 12 | Y |  | 2026-06-26 | 2026-06-29
| 1/2" Nylon Rope |  | 1 | Y |  | 2026-06-26
Project:
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date

## Elias's Crew
Project: | Miscellaneous
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
Silt Fence
Recycle Bins
Steel Bins
| 5 Gallon Metal Gas Cans | 3 | 3 | Y | Behind Ms. Laura's Office | 2026-06-17 | 2026-06-19
| 2" Rachet Straps | 6 | 6 | Y |  | 2026-06-23 | 2026-06-29
| Sand |  |  | Y
| 1" Rachet Straps | 6 | 6 | Y |  | 2026-06-23 | 2026-06-29
| Small Gangbox |  | 1 | Y |  | 2026-07-14 | 2026-07-14
| Male Plug End 15 amp / 125V |  | 20 | Y |  | 2026-07-14 | 2026-07-16
| Female Plug End 15 amp / 125V |  | 20 | Y |  | 2026-07-14 | 2026-07-17
| Weed Eater |  | 1 | Y
Project: | 0.095" Weed Easter String |  | 1 | N
| 10" 3 Cutter metal Blades |  | 1 | N
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date

## Ivan's Crew
Project: | Formwork For Troughs
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
Form Spray
Plywood
| 3/16" Masonite Plywood Sheet | 1 | 1 | Y | Outside Conex 2 | 2026-06-17 | 2026-06-18
| 3/4" Plywood | 10 | 10 | Y | TECO | N/A | N/A
| 3/4" 12" SDS Plus Masonry Drill Bit | 4 | 4 | Y |  | 2026-07-13
| 3/4" 18" SDS Plus Masonry Drill Bit | 2 | 2 | Y |  | 2026-07-13
| 316 Stainless Steel 5/8" Washer |  | 2 | N | McDade | 2026-07-22
| 316 Stainless Steel 5/8" Nut |  | 1 | N | McDade | 2026-07-22
| 316 Stainless Steel 5/8" Lock Washer |  | 2 | N | McDade | 2026-07-22
| 316 Stainless Steel 1/2" Washer |  | 1 | N | McDade | 2026-07-22
| 316 Stainless Steel 1/2" Nut |  | 2 | N | McDade | 2026-07-22
Project:
Miscellaneous
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
2" PVC
2" PVC 90s
| Whiskers | 25 | 25 | Y |  | 2026-06-29 | 2026-07-06
| 20 Oz Inverted Paint | 12 | 12 | Y |  | 2026-07-08 | 2026-07-16
| 1/2" x 2" x 48" Survey Stakes | 2 | 2 | Y |  | 2026-07-20
| 7/8" ANSI Hole Cleaning Brush | 6 |  | Y |  | 2026-07-20
| 5/8" ANSI Hole Cleaning Brush | 2 |  | Y |  | 2026-07-20

## Saul's Crew
Project: | FAS
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Wedge Anchors | 30 | 4 | Y |  | 2026-06-17 | 2026-06-18 | 2026-06-20
| 3/4"x8" Rebar Eater | 1 | 1 | Y |  | 2026-06-23 | 2026-06-29 | 2026-06-30
| Push Brooms |  | 1 | Y |  |  |  |  | Pick-up in Store
| 7/8”x1/2” Shank Drill bits for steel |  | 2 | N |  | 2026-07-16 |  | 2026-07-24
FBS
Project: | Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Pipe support Mk10 + Hardware |  |  | Y
| Pipe support Mk11 + Hardware |  |  | Y
| Pipe Support Mk12 + Hardware |  |  | Y
| 1" Mushroom Victaulic Flange Bolts | 60 | 24 | Y |  | 2026-06-19 | 2026-06-25 | 2026-06-25
| 1" x 8" Mason Drill Bits | 5 | 5 | Y |  | 2026-06-23
| 7/8" Mason Drill Bits | 3 | 5 | Y |  | 2026-06-23 | 2026-06-25 | 2026-06-25
| DeWalt Epoxy | 2 | 2 | Y |  | 2026-06-17 | 2026-06-18 | 2026-06-18
| DeWalt Epoxy Gun for 110 DeWalt Epoxy | 1 | 1 | Y | Ms. Laura | 2026-06-26 | 2026-06-29 | 2026-06-29
| Epoxy Straws |  | 12 | N |  | 2026-06-26
| 3/4" Anchor Bolts |  | 10 | Y |  | 2026-07-07 |  | 2026-06-29
| 3 ton Floor Jack |  | 1 | Y |  | 2026-07-07 | 2026-07-07 | 2026-07-07
| 10' x 10' Fire Blanket | 2 | 2 | Y |  | 2026-07-06 | 2026-07-07 | 2026-07-07
| 2 Eyebolts to screw onto anchors - Scott |  | 2 | Y |  | 2026-07-13 |  | 2026-07-24
| 8 oz Food Grade Anti Sieze | 6 | 6 | Y |  | 2026-07-09 | 2026-07-10 | 2026-07-24
| 3/4"x8" Wedge Anchors | 12 | 12 | Y |  | 2026-07-09 | 2026-07-09 | 2026-07-24
| Turbidity Analizers | Earliest Sept
Project: | Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| 1" Sch 80 PVC Pipe | 60 | 58.5' | Y |  | 2026-06-08 | 2026-06-23
| 3/4" Sch 80 PVC Pipe | 40 | 32.5' | Y |  | 2026-06-08 | 2026-06-23
| 1/2" Sch 80 PVC Pipe | 60 | 43.5' | Y |  | 2026-06-08 | 2026-06-23
| 1/2" Clear PVC | 20 | 4.5' | Y |  | 2026-06-08 | 2026-06-23
| 1/2" x 2" NPT FItting | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" x 4" NPT FItting | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" x 3" NPT Fitting | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| FPT Tee 1/2" | 12 | 12 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" SOC x FPT 90 | 12 | 12 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" SOC 90 | 30 | 30 | Y |  | 2026-06-08 | 2026-06-23
| 3/4" SOC 90 | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1"x1/2" SOC Tee | 18 | 18 | Y |  | 2026-06-08 | 2026-06-23
| 1"x3/4" SOC Tee | 12 | 12 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" SOC Tee | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1" SOC Tee | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" MPT x 3/8" Hose Connector | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" SOC Coupling | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1" SS NPT x PVC Socket Coupling | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" SPC x FPT Coupling | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1" Ball Valve | 6 | 6 | Y |  | 2026-06-08 | 2026-06-23
| 1/2" Ball Valve | 24 | 24 | Y |  | 2026-06-08 | 2026-06-23
DPD/DPS
Project: | Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date

## Laura's List
Project:
| Material Description | Qty. | Qty. Needed | Onsite (Y/N) | Location Onsite | Order Date | Delivery Date | Required by Date
| Loctite PL Adhesive 10 oz | 2 |  | Y |  | 2026-07-20
| Engine Oil 10 W30 4 Cycle | 4 |  | Y |  | 2026-07-20
| Sledge Hammer Handle | 4 |  | Y |  | 2026-07-20
| 3/4" Steel Strap | 2 |  | Y |  | 2026-07-17